## 1. Summary
Category | Detail
PROJECT | VTS – Verification Tracking System
UPGRADE | Angular 16 → Angular 17
DATE | 2026-06-12
NODE REQUIRED | Node.js 18.13+ (upgraded to v22.22.3)
TYPESCRIPT | ~4.x → ~5.4.2
RXJS | ^6.x (with rxjs-compat) → ^7.8.0 (no compat layer)
TOTAL PACKAGE CHANGES | 40+ packages updated / added / removed
TYPESCRIPT FILES CHANGED | 6 files
HTML TEMPLATE FILES CHANGED | 96+ files (@ symbol fix + scrollbar replacement)
NEW FILES CREATED | 1 file (filter.pipe.ts)
LEGEND
🟡 CHANGED | Version updated to Angular 17 compatible version
🟢 ADDED | New package added (not present in Angular 16)
🔴 REMOVED | Package removed (not Ivy-compatible or deprecated)
🟣 FIXED | Code fix required due to Angular 17 breaking change

## 2. Package Changes
# | Package Name | Old Version | New Version | Type | Reason / Notes
1 | @angular/animations | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
2 | @angular/cdk | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
3 | @angular/common | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
4 | @angular/core | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
5 | @angular/forms | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
6 | @angular/google-maps | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
7 | @angular/localize | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
8 | @angular/material | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
9 | @angular/platform-browser | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
10 | @angular/platform-browser-dynamic | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
11 | @angular/router | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 core upgrade
12 | @angular-devkit/build-angular | ^16.x | ^17.3.0 | 🟡 CHANGED | Build tool for Angular 17
13 | @angular-devkit/core | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 devkit
14 | @angular-devkit/schematics | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 devkit
15 | @angular/cli | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 CLI
16 | @angular/compiler | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 compiler
17 | @angular/compiler-cli | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 compiler-cli
18 | @angular/language-service | ^16.x | ^17.3.0 | 🟡 CHANGED | Angular 17 language service
19 | zone.js | ~0.13.x | ~0.14.3 | 🟡 CHANGED | Required by Angular 17
20 | typescript | ~4.9.x | ~5.4.2 | 🟡 CHANGED | Angular 17 requires TypeScript 5.x
21 | rxjs | ^6.x | ^7.8.0 | 🟡 CHANGED | Angular 17 requires RxJS 7; removed rxjs-compat
22 | @progress/kendo-angular-buttons | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
23 | @progress/kendo-angular-common | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
24 | @progress/kendo-angular-dateinputs | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
25 | @progress/kendo-angular-dialog | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
26 | @progress/kendo-angular-dropdowns | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
27 | @progress/kendo-angular-excel-export | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
28 | @progress/kendo-angular-grid | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
29 | @progress/kendo-angular-icons | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
30 | @progress/kendo-angular-inputs | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
31 | @progress/kendo-angular-intl | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
32 | @progress/kendo-angular-l10n | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
33 | @progress/kendo-angular-label | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
34 | @progress/kendo-angular-navigation | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
35 | @progress/kendo-angular-pdf-export | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
36 | @progress/kendo-angular-popup | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
37 | @progress/kendo-angular-treeview | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
38 | @progress/kendo-angular-utils | ^12.x | ^13.0.0 | 🟡 CHANGED | Kendo 13 supports Angular 17
39 | @progress/kendo-theme-default | ^4.x | ^6.4.0 | 🟡 CHANGED | Kendo theme for Angular 17
40 | @progress/kendo-angular-layout | (none) | ^13.0.0 | 🟢 ADDED | New required Kendo peer dependency for Angular 17
41 | @progress/kendo-angular-progressbar | (none) | ^13.0.0 | 🟢 ADDED | New required Kendo peer dependency for Angular 17
42 | primeng | ^9.x | ^17.18.0 | 🟡 CHANGED | PrimeNG 17 supports Angular 17
43 | primeicons | ^4.x | ^7.0.0 | 🟡 CHANGED | PrimeIcons 7 for PrimeNG 17
44 | angular-oauth2-oidc | ^12.x | ^17.0.0 | 🟡 CHANGED | Angular 17 compatible auth library
45 | angular-oauth2-oidc-jwks | ^12.x | ^17.0.0 | 🟡 CHANGED | Angular 17 compatible auth library
46 | @ngbracket/ngx-layout | ^12.x | ^17.0.0 | 🟡 CHANGED | Angular 17 compatible flex layout
47 | ngx-spinner | ^12.x | ^17.0.0 | 🟡 CHANGED | Angular 17 compatible spinner
48 | ngx-countdown | ^12.x | ^17.0.0 | 🟡 CHANGED | API change: CountdownGlobalConfig → COUNTDOWN_CONFIG
49 | @swimlane/ngx-charts | ^18.x | ^21.0.0 | 🟡 CHANGED | Angular 17 compatible charts
50 | angular-calendar | ^0.28.x | ^0.30.0 | 🟡 CHANGED | Angular 17 compatible calendar
51 | ngx-image-compress | ^12.x | ^15.1.6 | 🟡 CHANGED | Angular 17 compatible (no v16 exists)
52 | ngx-scanner-qrcode | ^1.3.x | 1.8.1 | 🟡 CHANGED | Module renamed to standalone component in 1.8.x
53 | @danielmoncada/angular-datetime-picker | (varies) | ^17.0.0 | 🟡 CHANGED | Angular 17 compatible datetime picker
54 | ngx-perfect-scrollbar | ^10.0.1 | REMOVED | 🔴 REMOVED | Not Ivy-compatible; abandoned. Replaced with <div style="overflow:auto">
55 | ng2-search-filter | ^0.5.1 | REMOVED | 🔴 REMOVED | Not Ivy-compatible. Replaced with custom FilterPipe
56 | jasmine-core | ~4.x | ~5.1.0 | 🟡 CHANGED | Angular 17 test framework update
57 | @types/jasmine | ~4.x | ~5.1.0 | 🟡 CHANGED | Angular 17 test types update

## 3. TS File Changes
# | File Path | Change Type | What Changed | Why (Breaking Change / Fix)
1 | package.json | 🟡 CHANGED | 40+ dependency versions updated. Added kendo-angular-layout, kendo-angular-progressbar. Removed ngx-perfect-scrollbar & ng2-search-filter usage. | Angular 17 requires updated compatible versions of all ecosystem packages
2 | tsconfig.json | 🟡 CHANGED | lib array changed from ["es2020","dom"] to ["ES2022","dom"] | Angular 17 / TypeScript 5.x targets ES2022 by default
3 | src/app/app.module.ts | 🟡 CHANGED | 1) Removed PerfectScrollbarModule import & provider 2) CountdownGlobalConfig → COUNTDOWN_CONFIG (API renamed in ngx-countdown v17) 3) NgxScannerQrcodeModule → NgxScannerQrcodeComponent (module became standalone component in v1.8.x) | 1) ngx-perfect-scrollbar not Ivy-compatible 2) ngx-countdown v17 renamed the config token 3) ngx-scanner-qrcode v1.8.x is a standalone component
4 | src/app/common-methods/modules/shared.module.ts | 🟡 CHANGED | 1) Removed PerfectScrollbarModule from imports/exports 2) Removed Ng2SearchPipeModule from imports 3) Added FilterPipe to declarations and exports | 1) ngx-perfect-scrollbar removed 2) ng2-search-filter not Ivy-compatible 3) Custom FilterPipe created as replacement
5 | src/app/common-methods/modules/material.module.ts | 🟡 CHANGED | Removed Ng2SearchPipeModule import and from MATERIAL_MODULES array | ng2-search-filter is not compatible with Angular 17 Ivy compiler
6 | src/app/common-methods/pipes/filter.pipe.ts | 🟢 NEW FILE | Created custom FilterPipe to replace ng2-search-filter. Filters array items by matching searchText against all property values. | ng2-search-filter was removed; a custom pipe was needed to maintain search functionality
7 | src/app/common-methods/components/invitation-creation/invitation-creation.component.ts | 🟣 FIXED | routePath property moved from class field initializer to ngOnInit(). Before: routePath = this.common.subCheckFlag !== true ? ... : ... After: routePath: string = ''; and set in ngOnInit() | TypeScript error TS2729: Property 'common' used before its own initialization. Angular 17 / TS5 is stricter about class field initialization order.
8 | src/app/invoice/preview-invoice/preview-invoice.component.ts | 🟣 FIXED | Fix 1: Moved initForGroupForAutoComplete() BEFORE getInvoiceClient() in ngOnInit() Fix 2: siteId and groupId initialized as disabled controls. Added .enable()/.disable() calls in siteName(). Removed [disabled] binding from template. | Fix 1: NG01052 – formGroup expects a FormGroup instance (template bound before form was created) Fix 2: Angular 17 warns that [disabled] on reactive form controls should use .enable()/.disable() instead

## 4. HTML Template Changes
# | Scope / Files Affected | File Count | Change Description | Before (Example) | After (Example) | Why
1 | All HTML templates with email addresses | 66+ files | Replaced @ symbol in email addresses with HTML entity &#64; | support@kryasolutions.com | support&#64;kryasolutions.com | Angular 17 introduced new @ block syntax (@if, @for, @switch). Any bare @ in templates is parsed as a control-flow block, causing NG5002 "Incomplete block" compile errors.
2 | generate-pdf.component.html | 1 file | Fixed double @ used as Kendo pager binding attribute | [@@Paging] | [&#64;&#64;Paging] | Same reason — Angular 17 @ syntax parser treats @@ as block syntax
3 | HTML templates with "we @" text pattern | ~30 files | Fixed space-prefixed @ in text content | we @ kryasolutions | we &#64; kryasolutions | Same reason — Angular 17 @ syntax
4 | HTML templates using <perfect-scrollbar> | ~30 files | Replaced <perfect-scrollbar> element with <div style="overflow:auto"> | <perfect-scrollbar [config]="config"> ... </perfect-scrollbar> | <div style="overflow:auto"> ... </div> | ngx-perfect-scrollbar is not Ivy-compatible and is abandoned. Removed the package; replaced the component with a plain scrollable div.
5 | preview-invoice.component.html | 1 file | Removed [disabled] attribute binding on two <mat-select> elements | <mat-select [formControl]="siteId" [disabled]="sitevalue?.length===0"> | <mat-select [formControl]="siteId"> | Angular 17 warns: do not use [disabled] with reactive form controls. Disable/enable state is now managed via FormControl.disable() and .enable() in the component.

## 5. Errors Fixed
# | Error Code / Message | File / Location | Root Cause | Fix Applied
1 | NG5002: Incomplete block | 66+ HTML template files | Angular 17 treats @ as control-flow block syntax (@if, @for, @switch). Email addresses and text with @ were parsed as broken blocks. | Replaced all @ symbols in email addresses and inline text with HTML entity &#64; across 66+ HTML files using PowerShell script.
2 | Module not found: ngx-perfect-scrollbar (not Ivy-compatible) | app.module.ts, shared.module.ts, 30+ HTML files | ngx-perfect-scrollbar library uses ViewEngine and is not compatible with Angular 17 Ivy compiler. | Removed PerfectScrollbarModule from all imports. Replaced all <perfect-scrollbar> tags with <div style="overflow:auto"> in 30+ templates.
3 | Module not found: Ng2SearchPipeModule (not Ivy-compatible) | shared.module.ts, material.module.ts | ng2-search-filter library is not Ivy-compatible with Angular 17. | Removed Ng2SearchPipeModule. Created a custom FilterPipe (filter.pipe.ts) as a drop-in replacement.
4 | CountdownGlobalConfig not exported (ngx-countdown v17) | app.module.ts | In ngx-countdown v17, the config token was renamed from CountdownGlobalConfig to COUNTDOWN_CONFIG. | Changed import and provider to use COUNTDOWN_CONFIG instead of CountdownGlobalConfig.
5 | NgxScannerQrcodeModule not found (v1.8.x) | app.module.ts | In ngx-scanner-qrcode v1.8.x, the NgxScannerQrcodeModule was replaced by a standalone NgxScannerQrcodeComponent. | Changed import from NgxScannerQrcodeModule to NgxScannerQrcodeComponent.
6 | TS2729: Property 'common' used before its initialization | invitation-creation.component.ts | TypeScript 5 / Angular 17 strict field initialization: class field tried to use injected service (this.common) before Angular had injected it. | Moved routePath initialization from class field declaration to ngOnInit() body.
7 | NG01052: formGroup expects a FormGroup instance | preview-invoice.component.ts (runtime) | In ngOnInit(), getInvoiceClient() was called before initForGroupForAutoComplete(). The HTTP call triggered change detection before invoiceClientListForm was created. | Reordered ngOnInit(): call initForGroupForAutoComplete() before getInvoiceClient().
8 | @progress/kendo-angular-layout not found | package.json (peer dependency) | Kendo UI v13 requires @progress/kendo-angular-layout as a peer dependency, which was not in the original package.json. | Added "@progress/kendo-angular-layout": "^13.0.0" to package.json.
9 | @progress/kendo-angular-progressbar not found | package.json (peer dependency) | Kendo UI v13 requires @progress/kendo-angular-progressbar as a peer dependency. | Added "@progress/kendo-angular-progressbar": "^13.0.0" to package.json.
10 | Node.js version too old (v12 / v16 in PATH) | Development environment | Angular 17 CLI requires Node.js 18.13 minimum. Old Node.js 12 from D:\node12\ was in PATH. | Installed Node.js v22.22.3 via NVM and refreshed PATH environment variable.
11 | npm ERR! kendo-licensing postinstall failure | npm install | Kendo license activation script failed during npm install. | Used npm install --legacy-peer-deps --ignore-scripts to skip the postinstall script.
12 | [disabled] attribute warning on reactive form | preview-invoice.component.html (runtime warning) | Angular 17 warns against using [disabled] attribute binding on reactive form controls. | Initialized siteId/groupId controls as disabled. Added .enable()/.disable() calls in siteName(). Removed [disabled] from template.

## 6. Infrastructure
# | Item | Before | After | Notes
1 | Node.js | v12.22.12 / v16.x | v22.22.3 (LTS) | Angular 17 minimum is Node 18.13+. Used NVM to manage multiple Node.js versions.
2 | Angular CLI | @angular/cli ^16.x | @angular/cli ^17.3.0 | Required for ng build / ng serve with Angular 17
3 | TypeScript | ~4.9.x | ~5.4.2 | Angular 17 requires TypeScript 5.x. Uses newer strict checks.
4 | RxJS | ^6.x + rxjs-compat | ^7.8.0 (no compat) | rxjs-compat shim removed. Code must use rxjs 7 imports directly.
5 | Build heap | --max_old_space_size=8192 | --max_old_space_size=8192 (kept) | Retained due to large project size. Required for successful build.
6 | Build time | ~90 sec (est.) | ~140 sec | Ivy full compilation; initial bundle ~36.85 MB
7 | Kendo UI | v12 (Angular 12) | v13 (Angular 17) | Major version bump. Two new peer deps added: kendo-angular-layout, kendo-angular-progressbar
8 | PrimeNG | v9 | v17.18.0 | Major version jump from 9 to 17 to match Angular 17